## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Notes Application (UI+API Testing)
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Dwasari Meghana
Approved By:
SCOPE
Features to be Tested:
1.Users login functionality (UI)
2.Note Creation via UI
3.Instant Note Display in UI
4.Retrive Notes via API (GET/notes)
5.UI to API Data Synchronization
6.Delete Note via API
7.API to UI Synchronization
8.Negative Scenarios for UI & API
TESTING TYPE
Functional Testing | Done
Regression Testing | Done
Integration Testing | Done
UAT | Done
TEST ENVIRONMENT
Environment: | QA
Browser/OS: | Google Chrome/ Windows
TIMELINE
Start Date: | 2026-05-05
End Date: | 2026-06-06
RESOURCES
QA Lead:
QA Resources: | Dwasari Meghana
Test Data Provider: | Self-generated test data
RISKS & ASSUMPTIONS
Risks: | 1.API server may be unavailable or slow | 2.Token authentication issues (401 errors) | 3.Network issues may affect testing | 4.UI may not sync instantly with API
Assumptions: | 2.Application is stable and accessible | 2.API endpoints are working correctly | 3.Valid test data is available | 4.User has proper login credentials

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | User Login | Check whether the user can log in with valid credentials | User account should exist
SC-002 | Create Note | Verify that the user can create a new note | User should be logged in
SC-003 | View Notes | Check whether created notes are displayed in the UI | At least one note should be available
SC-004 | Get Notes API | Verify that API returns list of all notes | User should have valid API token
SC-005 | UI to API Validation | Ensure note created in UI is visible in API response | Note should be created through UI
SC-006 | Delete Note API | Verify that note can be deleted using API | Note should already exist
SC-007 | API to UI Sync | Check whether deleted note is removed from UI | Note should be deleted via API
SC-008 | Validate API response time | Verify that the API response is received within 2 seconds | API should be accessible and user should have valid token
SC-009 | UI Negative | Check system behavior for invalid or empty inputs | No special condition required
SC-010 | API Negative | Verify API response for invalid requests or missing data | API should be accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Actual Result | Priority | Status
TC-001 | SC-001 | Login with valid credentials | Login page is opened | 1. Enter valid email 2. Enter valid password 3. Click Login | User should be logged in successfully and redirected to Notes page | User should be logged in successfully and redirected to Notes page | High | Pass
TC-002 | SC-001 | Login with invalid password | Login page is opened | 1. Enter valid email 2. Enter wrong password 3. Click Login | Error message should be displayed and user should not be logged in | Incorrect email address or password | High | Pass
TC-003 | SC-002 | Create note via UI | User is logged in | 1. Click Add Note 2.Enetr category 3. Enter title 4. Enter description 5. Click Save | Note should be created successfully | Note was created successfully and added to note list | High | Pass
TC-004 | SC-003 | Verify note appears instantly | Note is created | 1. Create a new note 2. Check notes list | Note should appear immediately without page refresh | Newly created notes is appered instantly in UI | High | Pass
TC-005 | SC-004 | Validate GET /notes API | Valid API token available | Send GET request to /notes | Send GET request to /notes | "success": true, "status": 200, "message": "Notes successfully retrieved" | High | Pass
TC-006 | SC-005 | Validate UI note in API | Note created via UI | 1. Create note in UI 2. Call GET /notes API 3. Compare title & description | UI created note should be present in API response | success": true, "status": 200, "message": "Notes successfully retrieved | High | Pass
TC-007 | SC-006 | Delete Note via API | Note exists in system | 1. Get note ID 2. Send DELETE request | Note should be deleted successfully | "success": true, "status": 200, "message": "Note successfully deleted" | High | Pass
TC-008 | SC-007 | Verify deleted note removed in UI | Note deleted via API | 1. Refresh UI 2. Check notes list | Deleted note should not appear in UI | Deleted note is not visible in UI after deletion | High | Pass
TC-009 | SC-008 | Validate API response time | API is accessible | 1. Send GET /notes request 2. Measure response time | API response time should be less than 2 seconds | API response received in 1.42 seconds, which is within the expected limit | Medium | Pass
TC-010 | SC-009 | Negative UI validation | Login page is opened | 1. Leave fields empty 2. Click Login | Error message should be displayed | Email address is required and Password is required | Medium | Pass
TC-011 | SC-010 | Negative API validation | API is accessible | Send request without token | API should return 401 Unauthorized error | "success": false, "status": 401, "message": "No authentication token specified in x-auth-token header" | Medium | Pass

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Email: meghanadwasari@gmail.com, Password: Meghana@0204 | Used for valid login scenarios
TD-002 | Invalid User | Email:meghana123a2gmail.com , Password: meghana@123 | Used for negative login testing
TD-003 | Empty Credentials | Email: "", Password: "" | Used to check validation for empty fields
TD-004 | Note Data (Valid) | Category:Work, Title: capgemini, Description: capgemini is a global leader consukting , technology, services and digital transformation company | Used for creating and validating notes
TD-005 | Note Data (Empty) | Title: "", Description: "" | Used for negative note creation test
TD-006 | Long Note Data | Title: Pytest, Description: Very long text content | Used to check field length handling
TD-007 | API Token (Valid) | Token: 903765e27ca54090b13a4b2e1f2cafa753b983718f8c4f1d8bcd807f6f2fd9b3 | Used for authorized API requests
TD-008 | API Token (Invalid) | Token: Invalid or expired token | Used for negative API testing (401 error)
TD-009 | Note ID | ID:69fa026581124e02985a7821 | Used for update and delete API operations

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Login with valid credentials | Dwasari Meghana | 2026-05-05 | Pass | DEF-001 | Logged in successfully and redirected to Notes page
TC-002 | Cycle-1 | Login with invalid password | Dwasari Meghana | 2026-05-05 | Pass |  | Proper error message displayed
TC-003 | Cycle-1 | Create note via UI | Dwasari Meghana | 2026-05-05 | Pass | DEF-002 | Note created successfully
TC-004 | Cycle-1 | Verify note appears instantly | Dwasari Meghana | 2026-05-05 | Pass |  | Note is visible immediately without refresh
TC-005 | Cycle-1 | Validate GET /notes API | Dwasari Meghana | 2026-05-05 | Pass |  | API returned notes list with status 200
TC-006 | Cycle-1 | Validate UI note in API | Dwasari Meghana | 2026-05-05 | Pass |  | UI created note is present in API response
TC-007 | Cycle-1 | Delete note via API | Dwasari Meghana | 2026-05-05 | Pass |  | Note deleted successfully using API
TC-008 | Cycle-1 | Verify deleted note removed in UI | Dwasari Meghana | 2026-05-05 | Pass |  | Deleted note is not visible in UI
TC-009 | Cycle-1 | Negative UI validation | Dwasari Meghana | 2026-05-05 | Pass |  | Error shown for empty login fields
TC-010 | Cycle-1 | Negative API validation | Dwasari Meghana | 2026-05-05 | Pass |  | API returned 401 Unauthorized error
TC-011 | Cycle-1 | Validate API response time | Dwasari Meghana | 2026-05-05 | Pass |  | Response received in 1.42 seconds (within limit)

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
REQ-001 | TC-001, TC-002 | UI login should work | Covered | Complete
REQ-002 | TC-003 | Create note via UI | Covered | Complete
REQ-003 | TC-004 | Note should appear instantly in UI list | Covered | Complete
REQ-004 | TC-005 | API GET /notes returns list | Covered | Complete
REQ-005 | TC-006 | UI-created note must appear in API | Covered | Complete
REQ-006 | TC-007 | Delete note via API | Covered | Complete
REQ-007 | TC-008 | Deleted note must disappear from UI | Covered | Complete
REQ-008 | TC-011 | API response time should be less than 2 seconds | Covered | Complete
REQ-009 | TC-009, TC-010 | Negative scenarios for UI and API | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-001 | Login success message not displayed | When user logs in successfully, no "Login successful" confirmation message shown | Medium | High | Open | Dev-User1 | 2026-05-05 | UI feedback missing after authentication
DEF-002 | TC-003 | Duplicate notes allowed with same title | Application allows creation of multiple notes with identical titles, causing confusion while identifying notes | High | High | Open | Dev-User2 | 2026-05-05 | Unique constraint validation missing

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes Aapplication (UI + API Testing)
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Dwasari Meghana
EXECUTION SUMMARY
Total Test Cases: | 11
Test Cases Executed: | 11
Test Cases Passed: | 11
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 1
Medium Defects: | 1
Low Defects: | 0
Open Defects: | 2
Closed Defects: | 0
CONCLUSION
Testing Status: | Completed
Release Readiness: | Not Ready for Release
Overall Recommendation: | Fix the identified High and Medium severity defects and perform regression testing before moving the application to production.
REMARKS
Build is not ready for release due to open high and medium severity defects affecting core functionality and user experience.